## Executive Summary
DevFlow — Internal Developer Platform · ROI Summary
As of: October 2024 ¦ Owner: Platform Engineering Team
Investment Summary
Total Investment to Date | 412000
– One-time Development Cost | 228000
– Cumulative Infrastructure (to Q3) | 184000
Annual Run Cost (current trajectory) | 222000
Annual Run Cost (budgeted) | 140400
ROI & Payback
Annual Productivity Value (Year 1) | 707000
Year 1 ROI | 125%
Payback Period Post-Launch | 7 months ✓
3-Year Projected ROI | 375%
Budget Variance Flags
Cost Line | Budgeted / month | Actual / month
Cloud Infrastructure | 8200 | 15400
Third-Party API Integrations | 3500 | 6800
Total Monthly Run Cost | 11700 | 22200
Engineering Leadership Go/No-Go Criteria
Criterion | Target | Status
Year 1 ROI > 80% | 80% | ✓ 125%
Payback Period < 12 months | < 12 months | ✓ 7 months
API Cost Variance Resolved | $0 variance | ✗ +$3,300/mo
Developer Adoption ≥ 90% | ≥ 90% | ✗ 68% (26/38)
Security Patching Current | 0 open CVEs | ✗ 3 open CVEs

## Cost Breakdown
Monthly Infrastructure & API Cost Trend — Jan to Oct 2024
Month | Infra Cost | API Cost | Total Monthly Cost | Budgeted Total | Variance
Jan 2024 | 8200 | 3500 | 11700 | 11700 | 0
Feb 2024 | 8900 | 3800 | 12700 | 11700 | 1000
Mar 2024 | 9400 | 4100 | 13500 | 11700 | 1800
Apr 2024 | 10200 | 4600 | 14800 | 11700 | 3100
May 2024 | 11800 | 5200 | 17000 | 11700 | 5300
Jun 2024 | 12900 | 5800 | 18700 | 11700 | 7000
Jul 2024 | 13600 | 6100 | 19700 | 11700 | 8000
Aug 2024 | 14200 | 6400 | 20600 | 11700 | 8900
Sep 2024 | 14800 | 6600 | 21400 | 11700 | 9700
Oct 2024 (proj) | 15400 | 6800 | 22200 | 11700 | 10500
Q3 Total (Jul–Sep) | 42600 | 19100 | 61700 | 35100 | 26600
One-Time Development Costs
Category | Cost
Engineering salaries (6 months) | 168000
Tooling licences & setup | 32000
Security & compliance review | 18000
Launch & migration support | 10000
Total Development Investment | 228000

## ROI & Projections
DevFlow ROI Model — Productivity Value & Scenario Analysis
Productivity Value Model
Developers actively using DevFlow | 38
Avg. time saved per developer per week | 4.2 hrs
Total hours saved per week | 158.4
Blended developer hourly rate | 85
Weekly productivity value | 13464
Annual productivity value (Year 1) | 707000
ROI Scenarios
Scenario | Year 1 ROI | Payback Period
Optimistic — API costs resolved, adoption 95% | 173% | 6 months
Base Case — current trajectory continues | 125% | 7 months
Conservative — costs rise + adoption stalls | 82% | 11 months
3-Year Forecast (Base Case)
Year | Annual Run Cost | Productivity Value | Net Annual Benefit | Cumulative ROI
Year 1 (2024) | 222000 | 707000 | 485000 | 117.7%
Year 2 (2025) | 196000 | 850000 | 654000 | 276.5%
Year 3 (2026) | 208000 | 1020000 | 812000 | 473.5%
3-Year NPV (8% discount rate, base case) |  |  |  | 1180000

## Risk Register
DevFlow Risk Register — Ordered High to Low Severity
Risk | Severity | Likelihood | Business Impact | Recommended Action | Owner
API cost overrun | High | High | $3,300/month over budget → $39,600/year; degrades Year 1 ROI by ~18 percentage points | Renegotiate vendor contract or evaluate open-source alternatives by Nov 2024 | Platform Lead
Security patching backlog | High | High | 3 unpatched CVEs in pipeline dependencies; audit failure blocks compliance sign-off | Schedule dedicated patch sprint within 30 days; block releases if unresolved by Nov 15 | Security Eng
Vendor lock-in — two core integrations | High | Medium | No fallback for CI orchestration API or artefact store; outage = full pipeline down | Evaluate open-source alternatives in Q4; document migration runbook | Arch Lead
Developer adoption gap | Medium | High | 12 of 38 developers still on legacy pipelines; reduces productivity value by ~30%, cutting ROI to ~82% | Mandate migration by end of Q4; assign dedicated onboarding support week | Eng Manager
Infrastructure scaling cost cliff | Medium | Medium | Infra costs jump ~80% at 60+ developers; ROI model breaks if headcount grows ahead of plan | Model scaling costs now; propose reserved-instance or spot-fleet strategy before Q1 hiring | Platform Lead
Documentation & onboarding debt | Low | High | Onboarding new devs takes 3× longer than planned; slows adoption and increases support load | Allocate 2 engineering weeks in Q4 to produce getting-started guide and runbooks | Senior Dev