## Executive Summary
ClearSpend Feature — Q3 Financial Projections
Regional Bank · Digital Product Group · Reporting Period: Q3 2026
KEY PROJECT METRICS
Total Investment to Date | $836,100
Q3 2026 Projected Spend | $268,600
Original LLM/API Budget (monthly) | $18,000
Current API Quotes (monthly) | $34,000
API Budget Variance | +$16,000 / month (+89%)
Projected Annual Benefit (Yr 1) | $543,000
Break-Even (Base Case) | ~14 months post-launch
Target Launch Date | Q1 2027
CFO DECISION CRITERIA
Total cost stays within $1.2M to launch | At Risk — currently tracking $1.14M; API overrun could push higher
Break-even achievable within 24 months | On Track — base case 14 months post-launch
Compliance sign-off before Q4 spend | Pending — legal review in progress
Security audit completed before launch | Not Started — vendor RFP to be issued Q3

## Cost Breakdown
ClearSpend — Cumulative Investment & Q3 Cost Breakdown
CUMULATIVE R&D INVESTMENT TO DATE
Quarter | Amount | Phase | Key Deliverables
Q4 2025 | $85,000 | Discovery & Planning | Market research, product scoping, initial wireframes
Q1 2026 | $184,500 | Design & Architecture | UX design, API selection, security framework
Q2 2026 | $298,000 | Core Development | Spending categorisation engine, bank API integration
Q3 2026 (projected) | $268,600 | Beta Development | Dashboard UI, alerts system, beta testing
Total | $836,100
Q3 2026 — DETAILED COST BREAKDOWN
Cost Category | Budgeted | Actual / Quote | Variance | Notes
Engineering salaries (8 FTE) | $162,000 | $162,000 | $0 | On budget
Third-party API — categorisation | $18,000 | $34,000 | +$16,000 | 89% over — renegotiation required
Cloud infrastructure (AWS) | $22,000 | $28,600 | +$6,600 | Higher usage during beta load testing
UX/Design contractor | $18,000 | $18,000 | $0 | Fixed contract — on budget
Security tooling | $8,000 | $12,000 | +$4,000 | Additional WAF licensing required
QA and test automation | $6,000 | $8,000 | +$2,000 | Expanded test coverage for compliance
Project tooling & licenses | $4,000 | $4,000 | $0 | On budget
Total Q3 | $238,000 | $266,600 | +$28,600 | 12% over Q3 budget

## ROI & Projections
ClearSpend — Return on Investment & 3-Year Projections
PROJECTED ANNUAL BENEFITS (YEAR 1 POST-LAUNCH)
Benefit Category | Basis | Annual Value
Reduced call-centre volume | 15% reduction in inbound calls about transactions | $187,000
Improved customer retention | 2% reduction in churn; avg customer LTV $8,400 | $210,000
Cross-sell conversion uplift | Dashboard surfaces relevant product offers | $98,000
Reduced manual statement queries | Fewer paper statement requests and branch visits | $48,000
Total Annual Benefit (Year 1) |  | $543,000
BREAK-EVEN SCENARIOS
Scenario | Total Investment | Annual Benefit | Break-Even | Notes
Optimistic | $836,100 | $680,000 | ~15 months | Full benefit realisation, API costs negotiated down
Base Case | $1,000,000 | $543,000 | ~22 months | Includes compliance and security cost contingency
Conservative | $1,200,000 | $380,000 | ~38 months | 50% benefit realisation; sustained API cost overrun
3-YEAR NET POSITION FORECAST
Period | Investment | Cumulative Benefit | Net Position | Notes
2026 (pre-launch) | $836,100 | $0 | -$836,100 | Development phase
2027 — Year 1 post-launch | $420,000 (ops) | $543,000 | -$713,100 | Partial-year launch Q1 2027
2028 — Year 2 | $420,000 (ops) | $600,000 | -$533,100 | Growing adoption
2029 — Year 3 | $420,000 (ops) | $660,000 | -$293,100 | Approaching net-positive
2030 — Year 4 (projected) | $420,000 (ops) | $720,000 | +$6,900 | Net positive — full ROI achieved

## Risk Register
ClearSpend — Financial Risk Register
Risk | Severity | Likelihood | Financial Impact | Mitigation | Owner
API/Integration cost overrun | High | High | +$192K annualised vs budget | Renegotiate volume contract; implement token optimisation sprint | Product + Engineering
Compliance sign-off delay | High | Medium | Delays launch by 4–8 weeks; deferred revenue | Engage legal immediately; parallel-path compliance review | Legal + Product
Security audit not scheduled | High | High | Cannot launch without; potential 6–8 week delay | Issue security vendor RFP this week | Engineering + IT Security
Hiring freeze — team capacity | Medium | High | Extended timeline pushes benefits to later quarters | Evaluate contract engineers for API integration work | HR + Product
Lower-than-expected adoption | Medium | Medium | Reduces Year 1 benefit by up to 40% | Phase rollout with early-adopter incentive; in-app onboarding flow | Product + Marketing
Competitive feature parity | Low | Medium | Reduces differentiation advantage | Prioritise unique features (savings goals, alerts) in MVP | Product Strategy